## Sheet1
IPD - Activity Log Book
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004190003 | Adithya Sanyal | Sudhir Bagul | 2021-03-04 | Review work done in last semester | Recap of what was done last semester and discussion of how to progress this semester | Brainstorm features & search for usable modules
2 | 60004190008 | Aditya Thaker | Sudhir Bagul | 2021-03-04 | Review work done in last semester |  | Brainstorm features & search for usable modules
3 | 60004190011 | Akshath Mahajan | Sudhir Bagul | 2021-03-04 | Review work done in last semester |  | Brainstorm features & search for usable modules
4 | 60004190003 | Adithya Sanyal | Sudhir Bagul | 2021-03-25 | Brainstorming of possible features | Discussion of the various features to be implemented, which tech stack to use, discussion on the different possible approaches | Review 1 super resolution technique and finalize
5 | 60004190008 | Aditya Thaker | Sudhir Bagul | 2021-03-25 | Explore usable modules and possible flow of app |  | Review 1 super resolution technique and finalize
6 | 60004190011 | Akshath Mahajan | Sudhir Bagul | 2021-03-25 | Review all possible approaches |  | Review 1 super resolution technique and finalize
7 | 60004190003 | Adithya Sanyal | Sudhir Bagul | 2021-04-10 | Explored Deep CNN approach | Discussion about what were the difficulties faced, dataset to be used, draft report of the project and discussion what approach will be best suited | Draft report on CNN
8 | 60004190008 | Aditya Thaker | Sudhir Bagul | 2021-04-10 | Explored local regression approach |  | Draft report on local regression
9 | 60004190011 | Akshath Mahajan | Sudhir Bagul | 2021-04-10 | Explored GAN approach |  | Draft report on GAN
10 | 60004190003 | Adithya Sanyal | Sudhir Bagul | 2021-04-17 | Draft report about DCNN approach and started searching for dataset | Further course of action as to how to proceed with the data acquisition, preprocessing and data handling part. Finalized GAN based approach | Implementation of GAN
11 | 60004190008 | Aditya Thaker | Sudhir Bagul | 2021-04-17 | Draft report on image reading and local regression approach |  | Search for datasets and design frontend
12 | 60004190011 | Akshath Mahajan | Sudhir Bagul | 2021-04-17 | Draft report created about GAN approach and downsampling |  | Search for datasets and look into downsampling
13 | 60004190003 | Adithya Sanyal | Sudhir Bagul | 2021-05-06 | Studied GAN implementation | Finalized datasets, Discussion about the presentation on the 10th of May, report preparation points | Report writing about implementation of GAN
14 | 60004190008 | Aditya Thaker | Sudhir Bagul | 2021-05-06 | Finalized design for website |  | Report writing about UI and design
15 | 60004190011 | Akshath Mahajan | Sudhir Bagul | 2021-05-06 | Explored and finalized div2k dataset |  | Report writing about div2k dataset